## Assumptions
ESCA Grant Amendment Assumptions
(To go with and explain spreadsheets)
Assumptions:
1. The implementation, oversight and/or management of the Long Term Obligations (LTOs) emanating from the Records of Decision remedies require one full-time (FTE) at the Program Manager (PM) level - to meet grant requirements while maintaining continuity and institutional knowledge.
2. The LTOs (Post-Closure MEC Find Assessment, Long Term Management and LUC Management) will all be performed by this FTE – with consulting support as needed.
3. The PM FTE must be supported by either one FTE Administrative position in FORA if extended or with partial FTEs in another organization with required combined skills set.
4. To ensure continuity and the ability to replace the PM FTE and Administrative FTE as needed, the LTO costs estimated at FORA fully-loaded rates.
5. The ESCA Grant Amendment yearly costs are calculated at Present Value (PV) and also Future Value (FV) based on when they occur over the life of the ESCA Grant.
6. The ESCA Grant Amendment has been estimated/calculated using a June 30, 2028 scenario.
7. ESCA LTO estimates are exclusive of regulatory reimbursement costs.
8. Future Value or Inflation Impact calculations are not incorporated in the LTO cost estimates unless specifically noted.
9. Assumes FORA Fiscal Year July1 to June 30.
10. Assumes FORA or comparable single successor continues past June 30, 2020.
11. Assumes full up-front payment for these costs with funds deposited in an interest bearing mechanism.
12. Cost estimated at one time and not subject to future increases.

## Sum Adm+Reg+LTO 8 yr(v2)
ESCA Work Flow | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Group 1
Fieldwork
Seaside CRUP Removal
County CRUP Removal
ESD
RI/FS
Proposed Plan
ROD
LUCIP/OMP
Site Closure
CERCLA Warranty
Out-Deed
Property Transfer
LTOs |  |  |  | Imp
Group 2
LUCIP/OMP
Site Closure
CERCLA Warranty
Out-Deed
Property Transfer
LTOs |  |  |  | Imp
Group 3
LUCIP/OMP
Site Closure
CERCLA Warranty
Out-Deed
Property Transfer
LTOs |  |  |  | Imp
Group 4
County CRUP Removal
RI/FS
Proposed Plan
ROD
LUCIP/OMP
Site Closure
CERCLA Warranty
Out-Deed
Property Transfer
LTOs |  |  |  | Imp
IAR
LUCIP/OMP
Site Closure
CERCLA Warranty
Out-Deed
Property Transfer
LTOs |  |  |  | Imp
FORA ESCA Program Archive
Grant Amendment per Year | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 (1/2yr) | Total
Regulator Reimbursement |  | 362023.2288 | 362023.2288 | [9 empty] | 724046.4577
Future Value (@2%) | 0 | 369263.6934 | 376648.9673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745912.6607 | Contractor
FORA Admin (April 1, 2017 - June 30, 2020) | 388058.9727 | 525411.9635 | 649575.0135 | 250705.9818 | [8 empty] | 1813751.9315
Future Value (@2%) | 388058.9727 | 535920.2028 | 675817.8441 | 266051.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865848.213
P-C MEC Assessments
Contractor |  |  |  | 18112.222 | 36224.4439 | 36224.4439 | 36224.4439 | 36224.4439 | 36224.4439 | 36224.4439 | 36224.4439 | 18112.222 | 289795.5515
Contract Support Staff during Assessments |  |  |  | 10620.7125 | 21241.425 | 21241.425 | 21241.425 | 21241.425 | 21241.425 | 21241.425 | 21241.425 | 10620.7125 | 169931.4
Subtotal | 0 | 0 | 0 | 28732.9345 | 57465.8689 | 57465.8689 | 57465.8689 | 57465.8689 | 57465.8689 | 57465.8689 | 57465.8689 | 28732.9345 | 459726.9515
Future Value (@2%) | 0 | 0 | 0 | 30491.6199 | 62202.9046 | 63446.9627 | 64715.902 | 66010.22 | 67330.4244 | 68677.0329 | 70050.5736 | 35725.7925 | 528651.4328 | Contractor
Long Term Management
FORA P-C MEC Assessments |  |  |  | 15358.2938 | 30716.5875 | 30716.5875 | 30716.5875 | 30716.5875 | 30716.5875 | 30716.5875 | 30716.5875 | 15358.2938 | 245732.7
FORA Long Term Management |  |  |  | 72269.0406 | 144538.0812 | 144538.0812 | 144538.0812 | 144538.0812 | 144538.0812 | 144538.0812 | 144538.0812 | 72269.0406 | 1156304.6496
Subtotal | 0 | 0 | 0 | 87627.3343 | 175254.6687 | 175254.6687 | 175254.6687 | 175254.6687 | 175254.6687 | 175254.6687 | 175254.6687 | 87627.3343 | 1402037.3496
Future Value (@2%) | 0 | 0 | 0 | 92990.8282 | 189701.2896 | 193495.3154 | 197365.2217 | 201312.5261 | 205338.7766 | 209445.5522 | 213634.4632 | 108953.5762 | 1612237.5493
LUC Management
FORA |  |  |  | 110842.9884 | 221685.9768 | 221685.9768 | 221685.9768 | 221685.9768 | 221685.9768 | 221685.9768 | 221685.9768 | 110842.9884 | 1773487.8145
Contractor |  |  |  | 2944.578 | 5889.156 | 5889.156 | 5889.156 | 5889.156 | 5889.156 | 5889.156 | 5889.156 | 2944.578 | 47113.248
Future Value (@2%) | 0 | 0 | 0 | 3124.8097 | 6374.6118 | 6502.1041 | 6632.1462 | 6764.7891 | 6900.0849 | 7038.0866 | 7178.8483 | 3661.2126 | 54176.6933 | Contractor
Subtotal | 0 | 0 | 0 | 113787.5664 | 227575.1328 | 227575.1328 | 227575.1328 | 227575.1328 | 227575.1328 | 227575.1328 | 227575.1328 | 113787.5664 | 1820601.0625
Future Value (@2%) | 0 | 0 | 0 | 120752.2758 | 246334.6426 | 251261.3354 | 256286.5621 | 261412.2934 | 266640.5392 | 271973.35 | 277412.817 | 141480.5367 | 2093554.3523
Grant Total
Present Value | 388058.9727 | 887435.1924 | 1011598.2424 | 480853.817 | 460295.6705 | 460295.6705 | 460295.6705 | 460295.6705 | 460295.6705 | 460295.6705 | 460295.6705 | 230147.8352 | 6220163.7528 | 70.08% | Total Percent of estimate given Army 3/17
Future Value (@2%) | 388058.9727 | 905183.8962 | 1052466.8114 | 510285.9174 | 498238.8368 | 508203.6135 | 518367.6858 | 528735.0395 | 539309.7403 | 550095.9351 | 561097.8538 | 286159.9055 | 6846204.2081
[13 empty] | 1328740.7868 | Contractor
| Total Hours | Annual staff hrs. | Asmnt Spt Staff | Contractor hrs
FORA P-C MEC Assessment | 3435 | 1083 | 1065 | 1181
FORA Long Term Management | 5096 | 5096 | 0 | 0
FORA LUC Management | 8408 | 7816 | 0 | 192
Total Hours | 16939 | 13995 | 1065 | 1373
8 years= hours |  | 14000
[13 empty] | 210000 | Equiptment
[13 empty] | 5307463.4213 | Personnel

## Reg. Reimburs Costs
| FY07/08 | FY08/09 | FY09/10 | FY10/11 | FY11/12 | FY12/13 | FY13/14 | FY14/15 | FY15/16 | FY16/17 | AVG FY
EPA Year invoice | 300000 | 119206 | 123941 | 193790 | 133735 | 122168 | 141452 | 162625 | 241473 | 114655 | 150338.3333
DTSC Year invoice | 0 | 146575 | 80520 | 118084 | 89903 | 114476 | 124450 | 96236 | 138799 | 278045 | 131898.6667 | To get to 2020 | 15% contingency | to get to 2020 with contingency | With LUCIP update work
EPA + DTSC Invoices |  | 265781 | 204461 | 311874 | 223638 | 236644 | 265902 | 258861 | 380272 | 392700 | 282237 | 564474 | 84671.1 | 649145.1 | 724046.4577
Regulator Funds
[9 empty] | At FORA | 181964
[9 empty] | Deposit with EPA | 300000
[9 empty] | Available FY15/16 | 481964
[9 empty] | Div. by FY Avg. | 282237
[8 empty] | Fund-Years Remaining | 1.7077 |  | Funds = Zero March, 2018
|  | FY08/09 | FY09/10 | FY10/11 | FY11/12 | FY12/13 | FY13/14 | FY14/15 | FY15/16
EPA Cumulative |  | 419206 | 543147 | 736937 | 870672 | 992840 | 1134292 | 1296917 | 1538390
DTSC Cumulative |  | 146575 | 227095 | 345179 | 435082 | 549558 | 674008 | 770244 | 909043
EPA + DTSC Cumulative |  | 565781 | 770242 | 1082116 | 1305754 | 1542398 | 1808300 | 2067161 | 2447433
ESCA Documents produced
Year |  | YR-2008 | YR-2009 | YR-2010 | YR-2011 | YR-2012 | YR-2013 | YR-2014 | YR-2015 |  | YR-2016
Docs per year |  | 10 | 14 | 12 | 15 | 11 | 26 | 15 | 14 |  | 17

## FORA Admin Costs updated
ESCA Work Flow | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01
Group 1
Fieldwork | bar: 2017-05-01 to 2017-06-01
Seaside CRUP Removal | bar: 2017-06-01 to 2018-05-01
County CRUP Removal | bar: 2017-05-01 to 2017-09-01
ESD | bar: 2017-08-01
RI/FS | bar: 2017-05-01 to 2017-10-01
Proposed Plan | bar: 2017-09-01
ROD | bar: 2017-07-01 to 2018-04-01
LUCIP/OMP | bar: 2018-02-01 to 2018-10-01
Site Closure | bar: 2018-09-01 to 2018-12-01
CERCLA Warranty | bar: 2019-01-01 to 2019-06-01
Out-Deed | bar: 2019-07-01
Property Transfer | bar: 2019-08-01 to 2019-09-01
Implement LTOs | bar: 2019-10-01 to 2020-06-01
Group 2
LUCIP/OMP | bar: 2017-05-01 to 2017-07-01
Site Closure | bar: 2017-06-01 to 2017-09-01
CERCLA Warranty | bar: 2017-10-01 to 2018-03-01
Out-Deed | bar: 2018-04-01
Property Transfer | bar: 2018-05-01 to 2018-06-01
Implement LTOs | bar: 2018-07-01 to 2020-06-01
Group 3
LUCIP/OMP
Site Closure | bar: 2017-05-01 to 2017-06-01
CERCLA Warranty | bar: 2017-07-01 to 2017-12-01
Out-Deed | bar: 2018-01-01
Property Transfer | bar: 2018-02-01 to 2018-03-01
Implement LTOs | bar: 2018-04-01 to 2020-06-01
Group 4
County CRUP Removal | bar: 2017-05-01 to 2017-09-01
RI/FS | bar: 2017-05-01 to 2017-07-01
Proposed Plan | bar: 2017-05-01 to 2017-10-01
ROD | bar: 2017-08-01 to 2018-04-01
LUCIP/OMP | bar: 2018-03-01 to 2018-10-01
Site Closure | bar: 2018-11-01 to 2018-12-01
CERCLA Warranty | bar: 2019-01-01 to 2019-06-01
Out-Deed | bar: 2019-07-01
Property Transfer | bar: 2019-08-01 to 2019-09-01
Implement LTOs | bar: 2019-10-01 to 2020-06-01
IAR
LUCIP/OMP | bar: 2017-05-01 to 2017-09-01
Site Closure | bar: 2017-10-01 to 2017-12-01
CERCLA Warranty | bar: 2018-01-01 to 2018-06-01
Out-Deed | bar: 2018-07-01
Property Transfer | bar: 2018-08-01 to 2018-09-01
Implement LTOs | bar: 2018-10-01 to 2020-06-01
Archive | bar: 2019-01-01 to 2020-06-01
| 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | Totals
Program Manager | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 19587.2903 | 763904.3208
Billing | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 340.3157 | 13272.3138
Exec. Officer | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 8694.8052 | 339097.4035
Controller | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 920.8849 | 35914.5096
Coordinator | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 12241.0342 | 477400.3338
Contractor/Legal Review | 2018-01-01: 12000; 2018-04-01: 12000; 2018-07-01: 12000; 2019-02-01: 98152.6; 2019-03-01: 26010.45; 2019-07-01: 12000; 2019-08-01: 12000 |  | 184163.05
Monthly Total | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 53784.3303 | 41784.3303 | 41784.3303 | 53784.3303 | 41784.3303 | 41784.3303 | 53784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 139936.9303 | 67794.7803 | 41784.3303 | 41784.3303 | 41784.3303 | 53784.3303 | 53784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 41784.3303 | 1813751.9315
Yearly Total | 2017-11-01: 2017; 2017-12-01: 388058.9727; 2018-11-01: 2018; 2018-12-01: 525411.9635; 2019-11-01: 2019; 2019-12-01: 649575.0135; 2020-05-01: 2020; 2020-06-01: 250705.9818
| FY 16-17 | FORA Rates with Fully Loaded Overhead
| Rate | [14 empty] | 2017-11-17
| Gross | Long | Pers ER | Flex | health | Medicare | SUI/ETT | Cell/Car | 457 | WC | Total | % of time | hourly | Admin Cost @17% | % Fully loaded Applied | Hourly 100% Fully Loaded | 3/17 version | Difference | Explanation
Program Manager | 2017-05-01: 81.9049; 2017-06-01: 8.1905; 2017-07-01: 15.7785; 2017-08-01: 0.99429; 2017-09-01: 5.6255; 2017-10-01: 1.0104; 2017-11-01: 0.052; 2017-12-01: 0.34286; 2018-01-01: 0; 2018-02-01: 0.90095; 2018-03-01: 114.7999; 2018-04-01: 100%; 2018-05-01: 114.7999; 2018-06-01: 19.516; 2018-07-01: 134.3159; 2018-08-01: 134.3159; 2018-09-01: 107.7957; 2018-10-01: 7.0042; 2018-11-01: Primarily due error in pension cost - employer bares full amount
Book Keeping | 2017-05-01: 30.39; 2017-06-01: 0; 2017-07-01: 2.1839; 2017-08-01: 0.99429; 2017-09-01: 5.6255; 2017-10-01: 0.34184; 2017-11-01: 0.052; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0.3039; 2018-03-01: 39.8914; 2018-04-01: 5%; 2018-05-01: 1.9946; 2018-06-01: 0.33908; 2018-07-01: 2.3336; 2018-08-01: 40.2305; 2018-09-01: 3.5318; 2018-10-01: -1.5373; 2018-11-01: Change in employee
Executive Officer | 2017-05-01: 136.6935; 2017-06-01: 13.6694; 2017-07-01: 26.3332; 2017-08-01: 0.99429; 2017-09-01: 10.3611; 2017-10-01: 1.6626; 2017-11-01: 0.052; 2017-12-01: 2.0571; 2018-01-01: 10.512; 2018-02-01: 1.5036; 2018-03-01: 203.8389; 2018-04-01: 25%; 2018-05-01: 50.9597; 2018-06-01: 8.6632; 2018-07-01: 59.6229; 2018-08-01: 212.5021; 2018-09-01: 48.463; 2018-10-01: 2.4968; 2018-11-01: Primarily due error in pension cost - employer bares full amount
Controller | 2017-05-01: 85.8048; 2017-07-01: 6.1662; 2017-08-01: 0.99429; 2017-09-01: 13.0903; 2017-10-01: 0.97937; 2017-11-01: 0.052; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0.85805; 2018-03-01: 107.945; 2018-04-01: 5%; 2018-05-01: 5.3973; 2018-06-01: 0.91753; 2018-07-01: 6.3148; 2018-08-01: 108.8625; 2018-09-01: 5.1498; 2018-10-01: 0.2474; 2018-11-01: Primarily due to change in wages effective 10/1/17
Coordinator/Assist. | 2017-05-01: 51.8235; 2017-06-01: 2.5912; 2017-07-01: 9.5297; 2017-08-01: 0.99429; 2017-09-01: 5.6255; 2017-10-01: 0.58368; 2017-11-01: 0.052; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0.54415; 2018-03-01: 71.744; 2018-04-01: 100%; 2018-05-01: 71.744; 2018-06-01: 12.1965; 2018-07-01: 83.9404; 2018-08-01: 83.9404; 2018-09-01: 67.6639; 2018-10-01: 4.0801; 2018-11-01: Primarily due error in pension cost - employer bares full amount
[14 empty] | Per hour cost of personnel | 286.5277 |  | 232.6042 |  | Other errors in Flex, health, Cell/Car and 457 used 2080 instead of 1750
Legal Review | 2018-05-01: 500
145.8333

## Post-Closure MEC Find Assesment
[5 empty] | FORA Admin (April 1, 2017 - June 30, 2020) Contract Support |  | FORA |  | Contractor |  | FORA Contract Support Staff
POST-CLOSURE MEC FIND ASSESSMENTS: FORA team was unable to estimate or foresee in 2006 the need for MEC find assessments, as remedy not selected or prescribed. Based on ESCA Grant requirements, remedies selected, Records of Decisions (ROD), and LUCIP/OMP, FORA MEC Find Assessment, Remedy Implementation responsibilities are Army obligations and should/may include: | Notes: * Also, requires Regulatory oversight funds to support tasks like: document reviews, meetings and site visits. | Units | Need | Cost with overhead, should = Fully loaded hourly wage + overhead for office, admin and supplies. | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Item Total For 2018-2028
IMPLEMENTATION - Setup Remedy
Develop standard format and procedures for MEC Find Assessments. | 30-50 hours of FORA time to develop + 10 hours to process comments and get approval. | hours | 50 | 245.3815 | 50 | 12269.075 |  | 0 |  |  |  |  | 12269.075
Provide/educate jurisdictions and land owners regarding MEC Find Assessments process, format and procedures. | One time - Jurisdiction staff + developer/outside agency staff x 7 jurisdictions at 4 hours each = 56 hours | hours | 56 | 245.3815 | 56 | 13741.364 |  | 0 |  |  |  |  | 13741.364
Total Implementation Costs | [12 empty] | 26010.439
OPERATION
Provide/educate jurisdictions, land owners and Unexploded Ordnance (UXO) contractors with MEC Find Assessments format and procedures. | Annually - meet with Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 2 hours each = 28 hours x 8 years = 224 hours | hours | 224 | 245.3815 |  |  |  | 0 | 224 | 54965.456 |  | 0 | 54965.456
Require MEC Find Assessment format and procedures in construction support plans. | 2 hrs. per CSP, Assume 3 CSPs per Major Improvement = 2 x 69 = 138 | hours | 138 | 245.3815 |  |  |  | 0 | 138 | 33862.647 |  |  | 33862.647
Collect MEC Find Assessment information from owner UXO-qualified contractor. | 2 hrs. per CSP, Assume 3 CSPs per Major Improvement = 2 x 69 = 138 | hours | 138 | 226.9 |  |  | 138 | 31312.2 |  | 0 |  |  | 31312.2
Notify Army, EPA and DTSC of MEC Finds. * | 1 hour per MEC find, Assume 39 finds per table to right (8 years) | hours | 39 | 226.9 |  |  | 39 | 8849.1 |  | 0 |  |  | 8849.1
Research Army and ESCA archives for previous MEC cleanup/find information - Contract to outside specialist. | 21 hours each x 39 Assessments | hours | 819 | 245.3815 |  |  |  | 0 | 819 | 200967.4485 |  | 0 | 200967.4485
Preform MEC Find Assessments -Document development |  |  |  | 245.3815 |  |  |  | 0 |  | 0 |  | 0 | 0
Provide Army, EPA and DTSC with MEC Find Assessments.* | 1 meeting x 2 hours x 39 assessments | hours | 78 | 226.9 |  |  | 78 | 17698.2 |  | 0 |  |  | 17698.2
Meet with Army, EPA and DTSC to present/clarify MEC Find Assessment.* | 1 meeting x 2 hours x 39 assessments | hours | 78 | 226.9 |  |  | 78 | 17698.2 |  | 0 |  |  | 17698.2
Receive Army, EPA and DTSC concurrence on MEC Find Assessment -OR- direction on additional investigation required.* | 1 meeting x 2 hours x 39 assessments | hours | 78 | 226.9 |  |  | 78 | 17698.2 |  | 0 |  |  | 17698.2
Inform jurisdiction and owner of concurrence or additional investigation required. | 2 meetings x 3 hour x 39 assessments | hours | 234 | 159.56 |  |  |  | 0 |  | 0 | 234 | 37337.04 | 37337.04
Total Operations costs | [12 empty] | 420388.4915
MAINTENANCE
Maintain files containing Army, EPA and DTSC MEC Assessment concurrence. | 15-25 hours per year x 8 years = 160 hours | hours | 160 | 159.56 |  |  |  | 0 |  | 0 | 160 | 25529.6 | 25529.6
Update/change MEC Find Assessments format and procedures as required. | 35-45 hours per year x 8 years = 320 hours | hours | 320 | 159.56 |  |  |  | 0 |  | 0 | 320 | 51059.2 | 51059.2
Continue to provide/educate jurisdictions, land owners and UXO contractors on the MEC Find Assessments format and procedures. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 2 hours each = 28 hours x 8 years = 224 hours | hours | 224 | 226.9 |  |  | 224 | 50825.6 |  | 0 |  | 0 | 50825.6
Total Maintenance costs | [12 empty] | 127414.4
MONITORING
Monitor jurisdictions, land owners and UXO contractors to insure they are implementing and following MEC Find Assessments format and procedures. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 4 hours each = 56 hours x 8 years = 448 hours | hours | 448 | 226.9 |  |  | 448 | 101651.2 |  | 0 |  | 0 | 101651.2
Total Monitoring costs | [12 empty] | 101651.2
INSPECTION
N/A | inspection would occur in activities above.
Total Inspection costs
REPORTING
Report MEC finds,* | 1 hour per MEC find, Assume 39 finds per table to right (8 years) | hours | 39 | 159.56 |  |  |  | 0 |  | 0 | 39 | 6222.84 | 6222.84
provide MEC Find Assessments Reports,* | 1 hour per MEC find, Assume 39 finds per table to right (8 years) | hours | 39 | 159.56 |  |  |  | 0 |  | 0 | 39 | 6222.84 | 6222.84
provide additional investigation results,* | 2 hours per MEC find, Assume 39 finds per table to right (8 years) | hours | 78 | 159.56 |  |  |  | 0 |  | 0 | 78 | 12445.68 | 12445.68
provide MEC Find Assessment records to Army, | 1 hour per MEC find, Assume 39 finds per table to right (8 years) | hours | 39 | 159.56 |  |  |  | 0 |  | 0 | 39 | 6222.84 | 6222.84
EPA and DTSC for CERCLA reporting,* | 2 hours per MEC find, Assume 39 finds per table to right (8 years) | hours | 78 | 159.56 |  |  |  | 0 |  | 0 | 78 | 12445.68 | 12445.68
Provide Army, EPA and DTSC with updated MEC Find Assessments format and procedures.* | 2 hours per MEC find, Assume 39 finds per table to right (8 years) | hours | 78 | 159.56 |  |  |  | 0 |  | 0 | 78 | 12445.68 | 12445.68
Total Reporting costs | [12 empty] | 56005.56
Total POST-CLOSURE MEC FIND ASSESSMENTS costs |  | Total Hours | 3435 |  | 106 | 26010.439 | 1083 | 245732.7 | 1181 | 289795.5515 | 1065 | 169931.4 | 731470.0905
Assumption - Total Number of Assessments on ESCA Property
Areas without RQA (Assume 2 Assessments per Major Improvement) | Major improvements reasonably anticipated | Assessments
Parker Flats Phase 1 | MPC, E-side Pkw, trails | 6
Parker Flats Phase II - trails | Trails | 2
County North | Commercial | 2
MOUT | Range relocation, fence install | 4
DRO/Monterey | Road widening, Park | 4
Laguna Seca Parking | Roads, parking lots | 4
CSUMB Off Campus -Trails | Trails | 2
Seaside | Park | 2
IAR Range 45 | Range, commercial | 4
Future East Garrison - Trails | Trails | 2
Areas with RQA (Assume 1 Assessments per Major Improvement) | Major improvements reasonably anticipated
Parker Flats Phase 1 | Endowment Parcels | 1
Parker Flats Phase II | County Development/Park | 1
Seaside | Seaside,1, 2, 3 & 4 | 4
Future East Garrison | East Garrison Housing | 1
| Total Number of Assessments | 39
Assumption - Total Number of Construction Support Plans (CSP) on ESCA Property
Areas without RQA (Assume 3 CSPs per Major Improvement) | Major improvements reasonably anticipated | CSPs
Parker Flats Phase 1 | MPC, E-side Pkw, trails | 9
Parker Flats Phase II - trails | Trails | 3
County North | Commercial | 3
MOUT | Range relocation, fence install | 6
DRO/Monterey | Road widening, Park | 6
Laguna Seca Parking | Roads, parking lots | 6
CSUMB Off Campus -Trails | Trails | 3
Seaside | Park | 3
IAR Range 45 | Range, commercial | 6
Future East Garrison - Trails | Trails | 3
Areas with RQA (Assume 3 CSPs per Major Improvement) | Major improvements reasonably anticipated
Parker Flats Phase 1 | Endowment Parcels | 3
Parker Flats Phase II | County Development/Park | 3
Seaside | Seaside,1, 2, 3 & 4 | 12
Future East Garrison | East Garrison Housing | 3
| Total Number of CSPs | 69

## Long Term Mgmnt 8y
FORA
LONG TERM MANAGEMENT: FORA team was unable to estimate or foresee in 2006, as remedy not selected or proscribed. Based on ESCA Grant requirements, remedies selected, RODs, and LUCIP/OMP FORA long term management responsibilities are Army obligations and should/may include: | * Also, requires Regulatory oversight funds to support tasks like: document reviews, meetings and site visits. | Units | Need | Cost with overhead, should = Fully loaded hourly wage + overhead for office, admin and supplies. | Hours | Cost | Item Total For 2018-2028
IMPLEMENTATION
Stewardship/O&M: Post-site closure long term obligations for review; monitoring; operations and maintenance activities, and reporting required to maintain remedy effectiveness.
Corrective actions necessary to assure effectiveness of LUC remedy. | N/A
Necessary changes to avoid future noncompliance. | N/A
Develop procedures and documents to notify Army, EPA and DTSC of: *
MEC-related data identified during property use. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
LUCIP/OMP inconsistencies, causes, and evaluate and implement necessary changes. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Sixty (60) day prior notice of conveyance of property - failure | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
LUCIP/OMP -failure | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Develop procedures and documents for Army, EPA and DTSC to: * |  |  |  |  | 0 | 0 | 0
Communicate, coordinate and track additional response actions. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Receive and transmit sixty (60) day property conveyance notice to other agencies, persons or entities to ensure LUCs implementation. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Develop procedures and documents for jurisdictions and owners to: |  |  |  |  | 0 | 0 | 0
Comply with LUC monitoring and reporting obligations. | 30 -50 hours | hours | 40 | 226.9048 | 40 | 9076.1915 | 9076.1915
Cease development when remedy not protective. Notify owner when able to recommence. | 30 -50 hours | hours | 40 | 226.9048 | 40 | 9076.1915 | 9076.1915
Develop procedures and documents for FORA to: |  |  |  |  | 0 | 0 | 0
Identify/report LUCIP/OMP inconsistency causes, evaluate and implement adjustments/modifications to avoid noncompliance. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Contract with UXO consultant and field staff to undertake additional response actions as required by EPA and DTSC. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Notify the jurisdictions/property owners of LUC responsibilities. | 10-20 hours | hours | 15 | 226.9048 | 15 | 3403.5718 | 3403.5718
Total Implementation costs | [6 empty] | 48784.5292
OPERATION
Provide/educate jurisdictions, land owners and qualified UXO contractors re:
Procedures and documents for annual land use control monitoring and reporting. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Notices of LUCIP/OMP violations and departures. | 1 hour per CSP, Assume 3 CSPs per Major Improvement = 1 x 69 = 69 hours | hours | 69 | 226.9048 | 69 | 15656.4303 | 15656.4303
Provide jurisdictions and owners with additional response/remedy modification information:
Notices of planned property conveyance. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
LUC enforcement. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Ensure jurisdictions and owners fulfill their LUC operation and maintenance obligations. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Inform Army, EPA and DTSC on failures of jurisdictions and land owners to perform: * Reg. Oversight = 8 hours per report (see below)
Annual land use control monitoring and reporting. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
LUCIP/OMP notifications. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Additional response/remedy modifications. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Notice of planned property conveyance. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
LUC enforcement. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Take action to:
Implement/enforce remedy modifications. | 4 hour per CSP = 4 x 69 = 276 | hours | 276 | 226.9048 | 276 | 62625.7212 | 62625.7212
Implement/conduct further response actions – if required under AOC and ESCA. | 4 hour per CSP = 4 x 69 = 276 | hours | 276 | 226.9048 | 276 | 62625.7212 | 62625.7212
For additional response actions and remedial actions:* Reg. Oversight and FORA paid by development
Process Explanations of Significant Difference (ESD) public outreach and documentation. | N/A | N/A |  |  |  |  | 0
Process ROD Amendments public outreach and documentation. | N/A | N/A |  |  |  |  | 0
Provide for ESD and ROD Amendments: Paid for by Development
Documentation. | N/A | N/A |  |  |  |  | 0
Public comment periods. | N/A | N/A |  |  |  |  | 0
Public meetings – with recorded public comments. | N/A | N/A |  |  |  |  | 0
Noticing. | N/A | N/A |  |  |  |  | 0
Alert and work with jurisdictions and property owners to: Seaside, DRO, County, CSUMB, Vets Cemetery., MPC, Monterey
Perform annual site inspections. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Review previous year’s building permits. | Annually - Jurisdiction 7 jurisdictions x 1 hours each x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Review previous year’s deeds. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Review previous year’s 911 call logs for MEC calls. | Annually - 8 hours x 8 years = 64 | hours | 64 | 226.9048 | 64 | 14521.9064 | 14521.9064
Review previous years MEC Recognition Safety Training records. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Review changed site conditions. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Alert and work with jurisdictions to develop annual LUC MEC reports. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Compile and submit annual LUC MEC reports to Army, EPA and DTSC.* | Annually - 2 hours to compile reports and submit x 8 years = 16 hours | hours | 16 | 226.9048 | 16 | 3630.4766 | 3630.4766
Respond to Army, EPA and DTSC annual LUC MEC report deficiency notices.* | Annually - 4 hours to compile reports and submit x 8 years = 32 hours | hours | 32 | 226.9048 | 32 | 7260.9532 | 7260.9532
Total Operations costs | [6 empty] | 534814.5828
MAINTENANCE
Update and notify jurisdictions, land owners, Army, EPA and DTSC of changes to:*
Requirements for reports on failures of jurisdictions and land owners to perform annual LUC monitoring and reporting. | In Operation above |  |  | N/A |  |  | 0
LUCIP/OMP ineffectiveness notifications. | In Operation above |  |  | N/A |  |  | 0
Additional response/remedy modification. | In Operation above |  |  | N/A |  |  | 0
Notice of planned property conveyance. | In Operation above |  |  | N/A |  |  | 0
LUC enforcement. | In Operation above |  |  | N/A |  |  | 0
Implement/enforce LUC non-compliance corrective actions.* | In Operation above |  |  | N/A |  |  | 0
Total Maintenance costs
MONITORING
Monitor deeds, jurisdictions and land owners to ensure compliance with requirements for:
Annual land monitoring and reporting. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
LUCIP/OMP ineffectiveness notifications; additional response/remedy modification. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Notice of planned property conveyance. | Semi-Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x7 x 2 x 8 years = 224 | hours | 224 | 226.9048 | 224 | 50826.6723 | 50826.6723
LUC enforcement. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Activities inconsistent with LUC Remedy objectives. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Monitor LUC non-compliance corrective actions. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9048 | 112 | 25413.3361 | 25413.3361
Total Monitoring Costs | [6 empty] | 177893.3529
INSPECTION
Periodic inspection of ESCA properties to confirm compliance with requirements for:
Changes in land use. | Annually - Jurisdiction 7 jurisdictions x 1 hours each x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Changes in site conditions. | Annually - Jurisdiction 7 jurisdictions at 1 hours each = 7 hours x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Ownership/occupancy changes. | Annually - Jurisdiction 7 jurisdictions at 1 hours each = 7 hours x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
MEC finds. | 4 hour per MEC Find , Assume MEC Finds per MEC Find Assessment assumptions (see below) = 4 x 39 = 156 | hours | 156 | 226.9048 | 156 | 35397.1468 | 35397.1468
LUC maintenance. | Annually - Jurisdiction 7 jurisdictions at 1 hours each = 7 hours x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
LUCIP/OMP ineffectiveness. | Annually - Jurisdiction 7 jurisdictions at 1 hours each = 7 hours x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Additional response/remedy modification. | Annually - Jurisdiction 7 jurisdictions x 1 hours each x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Notice of planned property conveyance. | In Monitoring Above |  |  | N/A |  |  | 0
LUC enforcement | In Monitoring Above |  |  | N/A |  |  | 0
Total Inspection costs | [6 empty] | 111637.1552
REPORTING
Reports on failures of jurisdictions and land owners to perform: *
Annual LUC monitoring and reporting. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9 | 112 | 25412.8 | 25412.8
LUCIP/OMP ineffectiveness notifications. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9 | 112 | 25412.8 | 25412.8
Additional response/remedy modification. | 8 hour per CSP, Assume 3 CSPs per Major Improvement = 8 x 69 = 552 | hours | 552 | 226.9048 | 552 | 125251.4424 | 125251.4424
Notice of planned property conveyance. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2 hours x 7 x 8 years = 112 | hours | 112 | 226.9 | 112 | 25412.8 | 25412.8
LUC enforcement. | Annually - Jurisdiction 7 jurisdictions x 1 hours each x 8 years = 56 hours | hours | 56 | 226.9048 | 56 | 12706.6681 | 12706.6681
Provide Army, EPA and DTSC with reports on: *
MEC-related data identified during property use. | In CSP Related Reporting above |  |  | N/A |  |  | 0
Activities inconsistent with LUCIP/OMP remedy objectives | In LUCIP/OMP ineffectiveness notifications above |  |  | N/A |  |  | 0
Changes made to comply with LUCs. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Upcoming property transfers. | In Notice of planned property transfers above |  |  | N/A |  |  | 0
LUC inconsistencies. | In LUCIP/OMP ineffectiveness notifications above |  |  | N/A |  |  | 0
LUC non-compliance. | In LUCIP/OMP ineffectiveness notifications above |  |  | N/A |  |  | 0
LUC non-compliance corrective actions. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Proposed additional response actions and remedy modifications. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Causes for inconsistences with LUC Remedy objective. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Evaluation of LUC Remedy objective inconsistencies. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Proposed changes to make to eliminate LUC remedy objective inconsistencies. | In LUC Enforcement and Additional response/remedy above |  |  | N/A |  |  | 0
Additional response actions and remedial objectives: * Reg. Oversight costs paid by Development
ESD documentation. | In Process ROD Amendments public outreach and documentation above |  |  | N/A |  |  | 0
Record of Decision\Amendment documentation. | In Process ROD Amendments public outreach and documentation above |  |  | N/A |  |  | 0
Provide jurisdictions and owners reports to support: | In Process Explanations of Significant Difference (ESD) public outreach and documentation above |  |  | N/A
Notices of non-compliance with LUCs. | Annually - Jurisdiction staff (1) + developer/outside agency staff (1) x 7 jurisdictions at 1 hours each = 2hrs x 7 x 8 years =112 hours | hours | 112 | 226.9 | 112 | 25412.8 | 25412.8
Army, EPA and DTSC review and approval of LUC compliance measures: *
Notice to cease development activities for non-compliance. | 8 hour per report per Major Improvement = 8 x 1 x 23 = 192 | hours | 192 | 226.9048 | 192 | 43565.7191 | 43565.7191
Total Reporting costs | [6 empty] | 283175.0295
Total Long Term Management |  | Total Hours | 5096 |  | 5096 | 1156304.6496 | 1156304.6496
Total contracted to outside specialists |  | Total Hours | 0 |  |  |  | 0
Assumption - Total Number of Assessments on ESCA Property
Areas without RQA (Assume 2 Assessments per Major Improvement) | Major improvements reasonably anticipated | Assessments
Parker Flats Phase 1 | MPC, E-side Parkway, trails | 6
Parker Flats Phase II - trails | Trails | 2
County North | Commercial | 2
MOUT | Range relocation, fence install | 4
DRO/Monterey | Road widening, Park | 4
Laguna Seca Parking | Roads, parking lots | 4
CSUMB Off Campus -Trails | Trails | 2
Seaside | Park | 2
IAR Range 45 | Range, commercial | 4
Future East Garrison - Trails | Trails | 2
Areas with RQA (Assume 1 Assessments per Major Improvement) | Major improvements reasonably anticipated
Parker Flats Phase 1 | Endowment Parcels | 1
Parker Flats Phase II | County Development/Park | 1
Seaside | Seaside,1, 2, 3 & 4 | 4
Future East Garrison | East Garrison Housing | 1
| Total Number of Assessments | 39
Assumption - Total Number of Construction Support Plans (CSP) on ESCA Property
Areas without RQA (Assume 3 CSPs per Major Improvement) | Major improvements reasonably anticipated | CSPs
Parker Flats Phase 1 | MPC, E-side Parkway, trails | 9
Parker Flats Phase II - trails | Trails | 3
County North | Commercial | 3
MOUT | Range relocation, fence install | 6
DRO/Monterey | Road widening, Park | 6
Laguna Seca Parking | Roads, parking lots | 6
CSUMB Off Campus -Trails | Trails | 3
Seaside | Park | 3
IAR Range 45 | Range, commercial | 6
Future East Garrison - Trails | Trails | 3
Areas with RQA (Assume 3 CSPs per Major Improvement) | Major improvements reasonably anticipated
Parker Flats Phase 1 | Endowment Parcels | 3
Parker Flats Phase II | County Development/Park | 3
Seaside | Seaside,1, 2, 3 & 4 | 12
Future East Garrison | East Garrison Housing | 3
| Total Number of CSPs | 69

## LUC Mgmnt 8y
[5 empty] | FORA Admin (April 1, 2017 - June 30, 2020) Contract Support |  | FORA |  | Contractor
LUC MANAGEMENT: FORA team was unable to estimate or foresee in 2006. Based on ESCA Grant requirements, remedies selected, RODs, and LUCIP/OMP FORA LUC responsibilities are Army obligations and should/may include: | * Also, requires Regulatory oversight funds to support tasks like: document reviews, meetings and site visits. | Units | Need | Cost with overhead, should = Fully loaded hours wage + overhead for office, admin and supplies. | Hours | Cost | Hours | Cost | Hours | Cost | Item Total For 2018-2037
IMPLEMENTATION
Develop procedures and documents with Army, EPA, DTSC and jurisdictions for:*
LUC requirement, monitoring, inspection, reporting, and enforcement. | FORA work with Regulators and Jurisdictions 2x40 hours = 80 hours | hours | 80 | 245.3815 | 80 | 19630.52 |  |  |  |  | 19630.52
MEC recognition safety training requirement, monitoring, inspection, reporting, enforcement. | FORA work with Regulators and Jurisdictions 2x40 hours = 80 hours | hours | 80 | 245.3815 | 80 | 19630.52 |  |  |  |  | 19630.52
UXO construction support requirement, monitoring, inspection, reporting, and enforcement. | FORA work with Regulators and Jurisdictions 2x40 hours = 80 hours | hours | 80 | 245.3815 | 80 | 19630.52 |  |  |  |  | 19630.52
Residential use restriction requirement, monitoring, inspection, reporting, and enforcement. | FORA work with Regulators and Jurisdictions 2x40 hours = 80 hours | hours | 80 | 245.3815 | 80 | 19630.52 |  |  |  |  | 19630.52
Failure to comply with LUC requirement, monitoring, inspection, reporting, and enforcement. | FORA work with Regulators and Jurisdictions 2x40 hours = 80 hours | hours | 80 | 245.3815 | 80 | 19630.52 |  |  |  |  | 19630.52
Total Implementation costs | [10 empty] | 98152.6
OPERATION
Review for Residential Use Restriction compliance:
Previous year’s property transfers. | FORA work with 7 Jurisdictions 1 hours ea. x 8 years = 56 hours | hours | 56 | 226.9048 |  |  | 56 | 12706.6681 |  | 0 | 12706.6681
Previous year’s property transfer deeds. | FORA work with 7 Jurisdictions 1 hours ea. x 8 years = 56 hours | hours | 56 | 226.9048 |  |  | 56 | 12706.6681 |  | 0 | 12706.6681
Previous year’s development projects. | FORA work with 7 Jurisdictions 1 hours ea. x 8 years = 56 hours | hours | 56 | 226.9048 |  |  | 56 | 12706.6681 |  | 0 | 12706.6681
Upcoming property transfers. | FORA work with 7 Jurisdictions 1 hours ea. x 8 years = 56 hours | hours | 56 | 226.9048 |  |  | 56 | 12706.6681 |  | 0 | 12706.6681
Upcoming development projects. | FORA work with 7 Jurisdictions 1 hours ea. x 8 years = 56 hours | hours | 56 | 226.9048 |  |  | 56 | 12706.6681 |  | 0 | 12706.6681
Compile materials for annual LUC Status Report for: |  |  |  | 226.9048
MEC Recognition Safety Training statistics. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Jurisdiction MEC Recognition Safety Training status. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
UXO Construction Support statistics. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Jurisdiction and owner construction support status. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Previous year’s development projects. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Previous year’s property transfer. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Coordination with jurisdictions, owners, Army, EPA and DTSC on: * Reg. Oversight paid for by development |  |  |  | 226.9048
Construction Support Requirements. | Jurisdictions 20 hours per CSP (69) = 1380 hours | hours | 1380 | 226.9048 |  |  | 1380 | 313128.6059 |  | 0 | 313128.6059
Anomaly Avoidance techniques. | Jurisdictions 1 hr. per month for 8 years =12 x 8 = 96 | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Work with and notify jurisdictions and property owners on: |  |  |  | 226.9048
Residential use restriction requirements for deeds. | FORA work with Jurisdictions 20 hours x 8 years = 160 hours | hours | 160 | 226.9048 |  |  | 160 | 36304.7659 |  | 0 | 36304.7659
Property owner residential use restriction obligations. | FORA work with Jurisdictions 20 hours x 8 years = 160 hours | hours | 160 | 226.9048 |  |  | 160 | 36304.7659 |  | 0 | 36304.7659
Verification of compliance with residential use restrictions. | FORA work with Jurisdictions 40 hours x 8 years = 320 hours | hours | 320 | 226.9048 |  |  | 320 | 72609.5318 |  | 0 | 72609.5318
Provide/educate jurisdictions, land owners and their qualified UXO contractors on the LUC, munitions recognition safety training, construction support, and residential use restrictions procedures and documents. | FORA with 7 Jurisdictions at 2 hours per year for 8 years = 7 x 2 x 8 years = 112 hours | hours | 112 | 226.9048 |  |  | 112 | 25413.3361 |  | 0 | 25413.3361
Inform Army, EPA and DTSC on failures of jurisdictions and land owners to perform LUC, munitions recognition safety training, construction support, and residential use restrictions procedures and documents. * | FORA 2 hours per half year for 8 years = 2 x 2 x 8 years = 32 hours | hours | 32 | 226.9048 |  |  | 32 | 7260.9532 |  | 0 | 7260.9532
Total Operations costs | [10 empty] | 1011995.3496
MAINTENANCE
Maintain MEC Recognition Safety Training:
Training materials. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Training records. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Training violation records. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Training corrective action records. MEC Safety Guide. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Web-based training materials- Contract to outside specialist. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 245.3815 |  |  |  |  | 96 | 23556.624 | 23556.624
Web-hosting services - Contract to outside specialist. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 245.3815 |  |  |  |  | 96 | 23556.624 | 23556.624
Maintain, update and notify jurisdictions, land owners, Army, EPA and DTSC of changes to: *
LUCs. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Munitions recognition safety training. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Construction support. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Residential use restrictions. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
LUC procedures. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
LUC documents. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Total Maintenance costs | [10 empty] | 264941.8434
MONITORING
Monitor deeds, jurisdictions and land owners to ensure conformity with requirements for LUC, munitions recognition safety training, construction support and residential use restrictions procedures and documents. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Monitor jurisdictions and owners during MEC Recognition Safety Training: | [9 empty] | 0
Jurisdiction training implementation. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Distribution of MEC Safety Guide. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Notification during Excavation Permit process. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Annual reporting. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Monitor jurisdiction and owner construction support implementation and enforcement through: | [9 empty] | 0
Digging and excavation ordinance. | FORA 4 hours per CSP (69) = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
Excavation Permit process. | FORA 4 hours per CSP (69) = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
Annual reporting. | FORA 4 hours per year for 8 years = 4 x 8 = 32 hours | hours | 32 | 226.9048 |  |  | 32 | 7260.9532 |  | 0 | 7260.9532
Total Monitoring costs | [10 empty] | 132512.3956
INSPECTION
Periodic inspection of ESCA properties to ensure conformity with requirements for: | [9 empty] | 0
LUCs | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
munitions recognition safety training, | FORA 1 hour per half year for 7 jurisdictions for 8 years = 1 x 2 x 7x 8 = 112 hours | hours | 112 | 226.9048 |  |  | 112 | 25413.3361 |  | 0 | 25413.3361
construction support, | FORA 1 hour per half year for 7 jurisdictions for 8 years = 1 x 2 x 7x 8 = 112 hours | hours | 112 | 226.9048 |  |  | 112 | 25413.3361 |  | 0 | 25413.3361
residential use restrictions procedures and documents. | FORA work with Jurisdictions 1 hours per month for 8 years = 1 x 12 x 8 = 96 hours | hours | 96 | 226.9048 |  |  | 96 | 21782.8595 |  | 0 | 21782.8595
Total Inspection costs | [10 empty] | 94392.3914
REPORTING
Reports to Army, EPA and DTSC of: *
MEC-related data Identified during construction support. | FORA based on Jurisdictions' info at 4 hours per CSP hours x 69 CSPs = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
Annual MEC Recognition Safety Training report. | FORA based on Jurisdictions' info at 4 hours per CSP hours x 69 CSPs = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
Annual MEC Construction Support report. | FORA based on Jurisdictions' info at 4 hours per CSP hours x 69 CSPs = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
MEC finds during Construction Support. | See Above | NA | [5 empty] | 0 |  | 0
Additional MEC investigations/actions. | FORA based on Jurisdictions' info at 4 hours per CSP hours x 69 CSPs = 276 hours | hours | 276 | 226.9048 |  |  | 276 | 62625.7212 |  | 0 | 62625.7212
Upcoming property transfers. | FORA based on Jurisdiction's Info at 2 hours per CSP (69) = 138 hours | hours | 138 | 226.9048 |  |  | 138 | 31312.8606 |  | 0 | 31312.8606
Past year’s property transfers. | FORA based on Jurisdiction's Info at 2 hour per year x 8 years = 16 hours | hours | 16 | 226.9048 |  |  | 16 | 3630.4766 |  | 0 | 3630.4766
Compliance with residential use restrictions. | FORA based on Jurisdiction's Info at 2 hours per CSP (69) = 138 hours | hours | 138 | 226.9048 |  |  | 138 | 31312.8606 |  | 0 | 31312.8606
Provide Army, EPA and DTSC with reports on Conformity/non-conformity with requirements for: *
LUC. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
munitions recognition safety training. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
construction support. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
residential use restrictions. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
procedures and documents. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Provide Army, EPA and DTSC with reports on Changes to requirements for: *
LUCs. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
munitions recognition safety training. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
construction support. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
residential use restrictions. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
procedures and documents. | In Operations and Maintenance sections above | N/A | [5 empty] | 0 |  | 0
Total LUC Management Costs | [10 empty] | 316759.0825
Total LUC Management Costs |  | Total Hours | 8408 |  | 400 | 98152.6 | 7816 | 1773487.8145 | 192 | 47113.248 | 1918753.6625
Assumption - Total Number of Assessments on ESCA Property
Areas without RQA (Assume 2 Assessments per Major Improvement) | Assessments
Parker Flats Phase 1 | 6
Parker Flats Phase II - trails | 2
County North | 2
MOUT | 4
DRO/Monterey | 4
Laguna Seca Parking | 4
CSUMB Off Campus -Trails | 2
Seaside | 2
IAR Range 45 | 4
Future East Garrison - Trails | 2
Areas with RQA (Assume 1 Assessments per Major Improvement)
Parker Flats Phase 1 | 1
Parker Flats Phase II | 1
Seaside | 4
Future East Garrison | 1
39
Assumption - Total Number of Construction Support Plans (CSP) on ESCA Property
Areas without RQA (Assume 3 CSPs per Major Improvement) | CSPs
Parker Flats Phase 1 | 9
Parker Flats Phase II - trails | 3
County North | 3
MOUT | 6
DRO/Monterey | 6
Laguna Seca Parking | 6
CSUMB Off Campus -Trails | 3
Seaside | 3
IAR Range 45 | 6
Future East Garrison - Trails | 3
Areas with RQA (Assume 3 CSPs per Major Improvement)
Parker Flats Phase 1 | 3
Parker Flats Phase II | 3
Seaside | 12
Future East Garrison | 3
69

## FORA Loaded Hourly
FORA Rates - Public | fully loaded
Program Manager | 134.3159
Coordinator/Assist. | 83.9404
Controller | 6.3148
Book Keeping | 2.3336
Total | 226.9048
ARCADIS Rates - Private |  | %
Program/Project Manager | 194.06 | 15% | 29.109
Senior Staff | 129.83 | 75% | 97.3725
Staff II | 118.9 | 100% | 118.9
| 442.79 |  | 245.3815
FORA Contract Support Staff during MEC Asses. |  | %
Contract Senior Staff | 129.83 | 100% | 129.83
Contract Staff II | 118.9 | 25% | 29.725
| 248.73 |  | 159.555